## Task Sheet-AIT664 Connecticut P
Tasks | Assigned To | % Allocation | Start Date | End Date | Health | Status | Notes
Define
Dataset exploration | Aravind Panchanathan, Divyansh Nigam, Mayuri Jadhav | 100% | 2024-02-02 | 2024-02-09 | Green | Complete
Research question finalization & defining objectives | Aravind Panchanathan, Divyansh Nigam, Mayuri Jadhav | 100% | 2024-02-02 | 2024-02-09 | Green | Complete
Exploring various data engineering tools | Aravind Panchanathan, Divyansh Nigam, Mayuri Jadhav | 100% | 2024-02-02 | 2024-02-09 | Green | Complete
Finalizing the data tools | Aravind Panchanathan, Divyansh Nigam, Mayuri Jadhav | 100% | 2024-02-02 | 2024-02-09 | Green | Complete
Design
Project Plan | Mayuri Jadhav | 100% | 2024-02-09 | 2024-02-16 | Green | Complete
Developing Data Architecture and Solution | Aravind Panchanathan | 100% | 2024-02-09 | 2024-02-16 | Green | Complete
Creating a full requirement document | Mayuri Jadhav | 100% | 2024-02-09 | 2024-02-16 | Green | Complete
Documentation
Project Topic | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-02-02 | 2024-02-09 | Green | Complete
Project proposal | Aravind Panchanathan, Divyansh Nigam, Mayuri Jadhav | 100% | 2024-02-02 | 2024-02-09 | Green | Complete
Abstract | Aravind Panchanathan, Divyansh Nigam, Mayuri Jadhav | 100% | 2024-02-09 | 2024-02-16 | Green | Complete
Project Presentation | Aravind Panchanathan, Divyansh Nigam, Mayuri Jadhav | 100% | 2024-04-19 | 2024-04-26 | Red | Not Started
A Working System | Aravind Panchanathan, Divyansh Nigam, Mayuri Jadhav | 100% | 2024-04-26 | 2024-05-04 | Red | Not Started
Computation Configurations
Create EC2 to instance | Aravind Panchanathan | 100% | 2024-02-16 | 2024-02-23 | Green | Complete
Create EC2 to S3 | Aravind Panchanathan | 100% | 2024-02-16 | 2024-02-23 | Green | Complete
Create S3 to Databricks | Aravind Panchanathan | 100% | 2024-02-16 | 2024-02-23 | Green | Complete
Create Databricks to Github | Aravind Panchanathan | 100% | 2024-02-16 | 2024-02-23 | Green | Complete
Create Databricks to S3 | Aravind Panchanathan | 100% | 2024-02-16 | 2024-02-23 | Green | Complete
Create S3 to QuickSight | Aravind Panchanathan | 100% | 2024-02-16 | 2024-02-23 | Green | Complete
Development and Deployment
Data Cleaning
Identify the Data | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Handle Missing Values | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Remove Duplicates | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Correct Data Types | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Standardize Data | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Normalize Data | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Handle Outliers | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Validate Data | Mayuri Jadhav | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Check for Consistency | Mayuri Jadhav | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Document Changes | Mayuri Jadhav | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Review and Iterate | Mayuri Jadhav | 100% | 2024-02-24 | 2024-03-02 | Green | Complete
Data Manipulation
Select Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Filter Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Sort Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Aggregate Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Merge Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Join Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Append Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Transpose Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Reshape Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Pivot Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Create Calculated Columns | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Normalize Data | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Handle Missing Values | Divyansh Nigam, Mayuri Jadhav | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Validate Data | Aravind Panchanathan | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Document Changes | Aravind Panchanathan | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Review and Iterate | Aravind Panchanathan | 100% | 2024-03-02 | 2024-03-09 | Green | Complete
Data Warehousing using Spark SQL
Design Data Model | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Extract Data | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Transform Data | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Load Data | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Index Data | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Manage Metadata | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Implement Security | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Monitor and Maintain | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Integrate Data | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Provide Access | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Evaluate and Improve | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-09 | 2024-03-16 | Yellow | In Progress
Data Exploration using PySpark and SQL
Initialize PySpark | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-16 | 2024-03-23 | Red | Not Started
Load Data | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-16 | 2024-03-23 | Red | Not Started
Explore Data Using PySpark | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-16 | 2024-03-23 | Red | Not Started
Visualize Data | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-16 | 2024-03-23 | Red | Not Started
Perform SQL Queries | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-16 | 2024-03-23 | Red | Not Started
Data Cleaning | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-16 | 2024-03-23 | Red | Not Started
Feature Engineering | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-16 | 2024-03-23 | Red | Not Started
Statistical Analysis | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-16 | 2024-03-23 | Red | Not Started
Iterate and Refine | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-16 | 2024-03-23 | Red | Not Started
Document Findings | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-16 | 2024-03-23 | Red | Not Started
Machine Learning - Regression model
Problem Definition | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Data Collection | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Data Preprocessing | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Split Data | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Feature Selection/Engineering | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Model Selection | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Model Training | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Model Evaluation | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Model Tuning | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Prediction | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Model Deployment | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Monitoring and Maintenance | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-03-23 | 2024-04-06 | Red | Not Started
Machine Learning - Clustering model
Problem Definition | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Data Collection | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Data Preprocessing | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Feature Selection/Engineering | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Choose a Clustering Algorithm | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Train the Clustering Model | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Cluster Assignment | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Evaluate the Clustering Model | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Interpret the Clusters | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Use the Clustering Model | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Model Deployment | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Monitoring and Maintenance | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-06 | 2024-04-13 | Red | Not Started
Machine Learning - Classification model
Problem Definition | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-14 | 2024-04-21 | Red | Not Started
Data Collection | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-14 | 2024-04-21 | Red | Not Started
Data Preprocessing | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-14 | 2024-04-21 | Red | Not Started
Feature Selection/Engineering | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-14 | 2024-04-21 | Red | Not Started
split data | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-14 | 2024-04-21 | Red | Not Started
Choose a Classification Algorithm | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-21 | 2024-04-28 | Red | Not Started
Train the Classification Model | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-21 | 2024-04-28 | Red | Not Started
Model Evaluation | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-21 | 2024-04-28 | Red | Not Started
Model Tuning | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-21 | 2024-04-28 | Red | Not Started
Prediction | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-21 | 2024-04-28 | Red | Not Started
Model Deployment | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-21 | 2024-04-28 | Red | Not Started
Monitoring and Maintenance | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-21 | 2024-04-28 | Red | Not Started
Steps For Checking The Biases In The Model Using Fairness 360 Tool
Install Fairness 360 | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-28 | 2024-05-02 | Red | Not Started
Import Required Modules | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-28 | 2024-05-02 | Red | Not Started
Load Model and Data | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-28 | 2024-05-02 | Red | Not Started
Define Bias Metrics | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-28 | 2024-05-02 | Red | Not Started
Check Bias | Aravind Panchanathan, Mayuri Jadhav | 100% | 2024-04-28 | 2024-05-02 | Red | Not Started
Generate Bias Report | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-28 | 2024-05-02 | Red | Not Started
Interpret Results | Aravind Panchanathan, Divyansh Nigam | 100% | 2024-04-28 | 2024-05-02 | Red | Not Started